## Project
Project Name : | AntLog
Client Name | Ralf Meyer

## AntLog Feature List
# | Main Feature | Sub Feature 1 | Sub Feature 1 | Description | Development Status | Development Comment | UAT Status | UAT Comment (if any) | Dev-Uat-Fix-1/in next-release | Ralf's Feedback Points
1 | General Operations (UI)
|  | Create New Folders |  |  | Done |  | ok
|  | Update Folders |  |  |  |  | ok
|  | Copy Folder |  |  | Done |  | ok
|  | Create New Files |  |  | Done |  | ok
|  | Open files |  |  | Done |  | ok
|  | Copy files |  |  | Done |  | ok
|  | Move files |  |  | Done |  | ok
|  | Delete files |  |  | Done |  | ok
|  | Create new AutoCAD layout |  | Only in conjunction with the Layout Manager plug-in | Out of scope
|  | Copy AutoCAD layouts |  | Only in conjunction with the Layout Manager plug-in | Out of scope
|  | Delete AutoCAD layouts |  | Only in conjunction with the Layout Manager plug-in | Out of scope
|  | Save folders & files as favourites |  |  | Done |  | ok
|  | Search Engine |  |  | Done |  | ok
|  |  | full-text search |  | Done |  | ok
|  |  | unlimited search options |  | Done |  | ok
|  | Email archive |  |  | Done |  | pending
|  |  | full-text search | by email content & subject | Done |  | pending
|  |  |  | by sender address | Done |  | pending
|  | Address management |  | assignment of address to each project | Done |  | ok
|  |  | Search & filter |  | Done | Query: In the address dialog, the search is working fine. Could you please clarify which address search you are referring to? |  | Search by address not possible | Already Working fine
|  |  | Linking of addresses |  | Done |  | ok
|  |  | Address group CRUD |  | Done | Could you please clarify the use case for enabling multi-select in the address search results? This will help us understand the requirement better and implement it accordingly. |  | Cannot select multiple records under address search | ralf will recall this and update soon
|  | Network drive management |  |  | Done
|  |  | Connect |  | Done |  | ok
|  |  | Disconnect |  | Done |  | ok
2 | Windows UI
|  | Minimize |  |  | Done |  | ok
|  | Maximize |  |  | Done |  | ok
|  | Close |  |  | Done |  | ok
|  | Title bar |  |  | Done |  | ok
|  | Window screen positioning |  | Using left mouse button & holding it, user will be able to position the window. | Done | It is working fine, and we can easily move both the dialog and the application window. | ?? | can not | It is working fine, and we can easily move both the dialog and the application window.
|  | Same size reopening |  |  | Done |  | ok
|  | Same location reopening |  |  | Done | Query | ok | What happens, when the resolution has changed and window is outside visible area? | ralf will share some demo or something so we can get a better idea about
|  | Last opened directory |  | Post startup | Done |  | ok
|  | Transparent display |  |  | Done
|  | Enable |  |  | Done |  | ok
|  | Disable |  |  | Done |  | ok
|  | Database folder path |  | User shall be able to view the folder path on selection. | Done |  | ok
|  | Database settings icon |  | User shall be able to update the database path of the selected files. | Done |  | ok
|  | Projects Home Screen |  | User shall be able to view all their folders and content therein on single screen of the Projects Homescreen. | Done |  | ok
|  | Folders |  | User shall be able to view the folder column | Done |  | ok
|  | Files |  | User shall be able to view the files under each selected folder | Done |  | ok
|  | Documents |  | User shall be able to view the documents inside selected files | Out of scope |  | ?? | Documents should be loaded from database
|  | Notes |  | User shall be able to view & edit notes as per folder / file / document selection. | Done |  | ok
|  | Text content of notes |  | Text box for notes | Done |  | ok
|  | Tooltip |  | Contains info about selected folder / file / document | Done | Tooltips for the folders and files are same as the old-antl syatem | ?? | There is no tooltip for files and folders | Tooltips for the folders and files are same as the old-antl syatem
|  | Pane resizer |  | User shall be able to resize the panes proporitonally. | Done |  | ok
|  | Navigation Options (Global) |  |  | Done
|  | Window resizer grip (dotted triangle at bottom right corner of Projects) |  | With the left mouse button pressed, you can change the total size of the dialog window | Done |  | ok
|  | Scroll bars |  |  | Done
|  |  | Horizontal |  | Done |  | ok
|  |  | Vertical |  | Done |  | ok
|  | Vertical Splitter |  | For resizing the favourites column height. | Done |  | ok
|  | Column Auto-fit |  | User can auto-size the columns width using this button. This arranges all the open columns equally. | Done |  | ok
|  | Refresh Button |  | User shall be able to trigger a refresh or update of the column display specifically syncing it with the latest commissioning data | Done |  | ok
|  | Reset column layout |  | User will be able to open closed columns & at the same time arrange them evenly. | Done |  | ok
|  | Filter |  |  | Done
|  | Folder Filters |  | User will be able to filter the folders. | Done
|  |  | All Folders |  | Done |  | ok
|  |  | Projects in system |  | Done |  | ok
|  | File Filters |  | User shall be able to choose between mentioned filters under files. | Done |  | ok
|  |  | Folder based Files | User shall have the functionality to filter files as per selected folder. | Done |  | ok
|  |  | All Files |  | Done
|  | Document Filters | File based Documents | User shall have the functionality to filter documents as per selected file. | Out of scope | Document panel is added in UI But Document panel can only be used in conjunction with Layout Manager plug-in (Layouts)
|  |  | All Documents |  | Out of scope
|  | Notes Filter |  |  | Done
|  |  | Subject | User will be able to filer notes under selected folder > file > document based on subject name. | Done |  | ok
|  | Navigation & Editing Columns |  |  | Done
|  | Folder |  |  | Done
|  |  | CRUD | User will be able to perform CRUD operations on folders. | Done
|  |  | Folder Properties | Selecting this will open a dialog box to edit the project properties. | Done |  | ok
|  |  | Show Project List | User shall be able to retroactively edit the Project Manager database. This allows entire projects that were mistakenly saved in the Project Manager to be deleted from the database. | Done |  | ok
|  | Files |  |  | Done
|  |  | Add Entry | User will be able to create a new file in the selected files. | Done |  | ok
|  |  | Delete Entry | User will be able to delete the selected file. Once delete is selected, the file on disk and entry for deleted file in the system database will be deleted on verification from user via pop-up. | Done |  | ok
|  |  | Copy Entry | User will be able to copy the selected file and add into the same folder with indexing into new files. | Done |  | ok
|  |  | File Properties | User will be able to update the properties as per mentioned fields. | Done |  | ok
|  |  | File type |  | Done |  | ok
|  |  | File Name |  | Done |  | ok
|  |  | File Path |  | Done |  | ok
|  |  | Profile (dropdown) |  | Done |  | ok | Profile has no function yet | Done | Please see Test-Notes
|  |  | File User |  | Done |  | ok
|  |  | Date Picker |  | Done |  | ok
|  |  | Action buttons |  | Done |  | ok
|  |  | Ok |  | Done |  | ok
|  |  | Cancel |  | Done |  | ok
|  |  | Change View | User shall be able to change the view of file entries. By default the view shall be detailed view for better clarity. | Done |  | ok
|  |  | List View |  | Done |  | ok
|  |  | Detailed View |  | Done |  | ok
|  |  | Large Icon |  | Done |  | ok
|  |  | Small Icon |  | Done |  | ok
|  |  | Tile View |  | Done |  | ok
|  | Documents |  | The documents column is primarily used in conjunction with CAD program in Layout Manager. | Out of scope
|  | Notes |  | User will be able to create notes for Folders, Files and Documents. | Done | Notes cannot be applied to Documents because the AutoCAD layout is not visible (the LayoutManager plugin is out of scope), so layouts are not shown in the document panel and notes cannot be created; the Documents column is primarily used with the CAD program via Layout Manager. |  |  | Notes cannot be applied to Documents because the AutoCAD layout is not visible (the LayoutManager plugin is out of scope), so layouts are not shown in the document panel and notes cannot be created; the Documents column is primarily used with the CAD program via Layout Manager. | The Layouts (tbDocuments) and threre notes must be visible also without Layoutmanager plugin
|  |  | Create new note |  | Done |  | ok
|  |  | Note No. | Text box | Done |  | ok
|  |  | Index | Dropdown | Done |  | ok
|  |  | Note Type | Dropdown | Done |  | ok
|  |  | Date Picker |  | Done |  | ok
|  |  | Start time | Time Picker | Done |  |  | AM/PM must be unvisible if time format is 24 hrs | Done
|  |  | End time | Time Picker | Done |  |  | Dito selecting hours: must have 24 h | Done
|  |  | Hours | Numerical text box | Done |  | ok
|  |  | Contact | Dropdown | Done |  |  | Contact cannot be selected anyway there is some configured | Done
|  |  | Title | Title Name | Done |  | ok
|  |  | Description Editor |  | Done |  | ok
|  |  | Bold |  | Done |  | ok
|  |  | Italics |  | Done |  | ok
|  |  | Alignment |  | Done |  | ok
|  |  | Font |  | Done |  | ok
|  |  | Display Notes | User shall be able to view all the notes as per selected folder / file / document. | Done |  |  | Windows should close with ESC key (ask to save if something has changed) | Done
|  |  | Edit Notes | User shall be able to edit the notes on double-clicking. | Done |  | ok
|  |  | Change Logging | User shall be able to enter a detailed description when editing any AutoCAD file. | Done
|  |  | Note No. | Text box | Done |  | ok
|  |  | Index | Dropdown | Done
|  |  | Note Type | Dropdown | Done
|  |  | Date Picker |  | Done
|  |  | Start time | Time Picker | Done
|  |  | End time | Time Picker | Done
|  |  | Hours | Numerical text box | Done
|  |  | Contact | Dropdown | Done
|  |  | Title | Title Name shall be taken up automatically as per the Author of AutoCAD file. | Done | Title field is working for folders/files Notes but it cannot be applied to Documents because the AutoCAD layout is not visible (the LayoutManager plugin is out of scope), so layouts are not shown in the document panel and notes cannot be created; the Documents column is primarily used with the CAD program via Layout Manager.
|  |  | Description Editor |  | Done |  |  | How can I translate the style/font dialog | Done
|  |  | Bold |  | Done |  | ok
|  |  | Italics |  | Done |  | ok
|  |  | Alignment |  | Done |  | ok
|  |  | Font |  | Done |  | ok
|  |  | Copy Notes | User shall be able to copy notes. | Done |  | ok
|  |  | Delete Notes | User shall be able to delete notes. | Done |  | ok
|  |  | Notes Properties | User shall be able to notes properties. | Done |  | ok
|  | Folder Hierarchy |  | In Antlog Projects, the user shall be able to view the hierarchy as mentioned in previous column. | Done
|  |  | Create Folders | User shall be able to create folders. | Done |  | ok
|  |  | Set Hierarchy | User shall be able to set hierarchy. | Done
|  |  | Area | User shall be able to area. | Done |  | ok
|  |  | Project | User shall be able to project. | Done |  | ok
|  |  | Sub-project | User shall be able to sub-project. | Done |  | ok
|  | Create a Space |  | Once connection with the shared network is established, user shall be able to create a space for sharing data with other users in the same network. Since space is the highest level of folder structure, the user shall be able to create space if no space exists. If any space already exists, then the user shall be able to create a project. | Done |  | ok
|  |  | Select Drive / Folder | User shall be able to select drive / folder and right click on it to create a space. | Done |  | ok
|  |  | Configure Space | User shall be able to configure the editable settings of a space | Done |  | ok
|  |  | Parent | Parent info | Done |  | ok
|  |  | Location | Auto-locate in database | Done |  | ok
|  |  | Save to database check box | User shall have the option to save the space in database. | Done |  | ok
|  |  | Project Info |  | Done |  | ok
|  |  | Name | Textbox | Done |  | ok
|  |  | Inherit from Parent Folder check box | User shall have the option to inherit the name details from parent folder. | Done |  | ok | Must be tested with Layoutmanager
|  |  | Number | Numerical text box | Done |  | ok
|  |  | Start Date | Date Picker | Done |  | ok | Please note the date format. | Done
|  |  | End Date | Date Picker | Done |  | ok | dito | Done
|  |  | Status | Dropdown | Done |  | ok | removed | Already discussed ! We have decided to remove the dropdown field as it does not contain any data.
|  |  | Folder Info |  | Done |  | ok
|  |  | Function | Dropdown | Done |  | ok
|  |  | Remarks | Textbox | Done |  | ok
|  |  | User | Auto-detected | Done |  | ok
|  |  | Action buttons |  | Done |  | ok
|  |  | Ok |  | Done |  | ok
|  |  | Apply |  | Done |  | ok
|  |  | Cancel |  | Done |  | ok
|  | Create a folder | Same form as "Create a space" | User shall be able to create a folder under space with above shared configurations. | Done |  | ok
|  | Create a sub-folder | Same form as "Create a space" | User shall be able to create a sub-folder under space with above shared configurations. | Done |  | ok
|  | Sub-folder structure as a template |  | User shall have the functionality to define templates for all the sub-folders and apply these templates to the existing / new sub-folders. | Done |  | ok
|  |  | Select sub-folder | User shall be able to select & right-click on the sub-folder to move into properties. | Done |  | ok
|  |  | Defaults tab | User shall be able to select the defaults tab. | Done |  | ok
|  |  | Copy content into new project |  | Done |  | ok
|  |  | Selection button |  | Done |  | ok
|  |  | Select from the available folder templates |  | Done |  | ok
|  |  | Action buttons |  | Done |  | ok
|  |  | Ok |  | Done |  | ok
|  |  | Cancel |  | Done |  | ok
|  |  | Create new folder |  | Done |  | ok
|  | Create sub-project | Same form as "Create a space" | User shall be able to create sub-project if the project needs to be divided into smaller and manageable sub-projects. This functionality shall work when user right-clicks on the project & select "New Folder" command. | Done |  | ok
|  | Import existing folder into system |  | User shall be able to import the folders into system database by right-clicking on the folder and selecting the "Save to database" command. | Done |  | ok
|  |  | Select folder |  | Done |  | ok
|  |  | Select save to database |  | Done |  | ok
|  | Show projects list |  | User shall be able to edit the database entries via show project list command. | Done |  | ok | Long time to load, please add animation | Done
|  |  | View list | User shall be able to view a table for project list as per mentioned columns. | Done | The list is currently sorted by ID by default. Users can switch between ascending and descending order as needed. | ok | sorted in ascending order as default, please | Done
|  |  | ID |  | Done |  | ok
|  |  | Location |  | Done |  | ok
|  |  | Item |  | Done |  | ok
|  |  | Delete item | User shall be able to delete the selected item. | Done |  | ok | After deleting a record, list must be refreshed | Already Working, but need to confirm from your side .
|  |  | Confirmation pop-up |  | Done |  | ok | With deleting a project record, inherit sub-projects must also be deleted | Done
|  |  | Search & filter | User shall be able to search & filter the projects. | Done |  | ok | see additional remarks | Already Working, but need to confirm from your side .
|  |  | Edit list | User shall be able to edit the columns and rows that have white background. Uneditable entries are marked grey for better clarity. | Done |  | ok
|  | Create new files |  | User shall be able to create new files | Done |  | ok
|  |  | Template setup | User shall be able to setup the templates for resuability purposes. | Done |  | ok
|  |  | Add template |  | Done |  | ok
|  |  | View tempalte |  | Done |  | ok
|  |  | Description |  | Done |  | ok
|  |  | Extension |  | Done |  | ok
|  |  | Filepath |  | Done |  | ok
|  |  | Profiles |  | Done |  | ok
|  |  | Edit template |  | Done |  | ok | Cannot order by column | Query Discussed :- In the legacy application, the Template tab in the Options dialog does not have ascending/descending sorting functionality. Please confirm if you want us to add this behavior in the new application. | Done need to add sorting in that table
|  |  | Template type | The template types are static in nature and shall be visible as a dropdown with pre-defined formats i.e., 1. .bmp 2. .jpg 3. .dwg 4. .xls 5. .doc 6. .pdf 7. .txt 8. .docx 9. .xlsx 10. mp3x 11. .mov 12. .pps | Done |  | ok
|  |  | Template dropdown | Dropdown to link the new template to any of the existing tempalates within user's computer. | Done |  | ok
|  |  | Profile Name | Textbox | Done |  | ok
|  |  | User | Textbox | Done |  | ok
|  |  | Date | Date Picker | Done |  | ok
|  |  | Action buttons |  | Done |  | ok
|  |  | Ok |  | Done |  | ok
|  |  | Cancel |  | Done |  | ok
|  | Copy / Move - Files |  |  | Done |  | ok
|  |  | Green Arrow Button | User shall be able to access second folder via green navigation button for managing the copy, move and panel operations on files. | Done |  | ok
|  |  | Homescreen | User shall be able to view the enhanced version of Homescreen in which all the 4 columns shall be replicated so that user can drag & drop the files easily from one location to another. Hence, user will be able to view 8 panes on homescreen. | Done |  | ok
|  |  | Copy Files |  | Done |  | ok
|  |  | Select File | User shall be able to select the file that needs to be copied from source location. | Done |  | ok
|  |  | Drag | User shall be able to drag using the left click to the desired destination. | Done |  | ok
|  |  | Drop | User shall be able to drop using by unholding the left click onto the desired destination. | Done |  | ok | dialog should close after copy/move | Done
|  |  | File configuration options |  | Done |  | ok
|  |  | Rename File |  | Done |  | ok
|  |  | Prefix Checkbox | User can automatically add current date as prefix using this checkbox. | Done |  | ok
|  |  | Add Prefix | Textbox | Done |  | ok
|  |  | Add Suffix | Textbox | Done |  | ok
|  |  | Database |  | Done |  | ok
|  |  | Copy with data (always move with) | Checkbox | Done |  | ok
|  |  | Replace without warning | Checkbox | Done |  | ok
|  |  | Action buttons |  | Done |  | ok
|  |  | Copy here |  | Done |  | ok
|  |  | Move here |  | Done |  | ok
|  |  | Cancel |  | Done |  | ok
|  |  | Progress Status | User shall be able to view the progress statuses on moving / copying the files from source to destination. | Done |  | ok
|  |  | From | File source | Done |  | ok
|  |  | To | File desination | Done |  | ok
|  |  | File Count | No. of files copied / moved out of total files selected for the operation. | Done |  | ok
|  |  | Close after process | Checkbox to auto-close the progress status bar once the copying / moving process is completed | Done |  | ok
|  |  | Cancel | Cancel the operation | Done |  | ok
|  |  | List View | View files with green tick mark that are copied / moved. | Done |  | ok
|  |  | Horizontal Scrollbar | Scrollbar to view the entire file name. | Done |  | ok
|  | Email |  |  | Done | The Outlook Email Integration feature allows users to import their Outlook emails directly into the application and organize them within the file system and database. Since the latest Outlook desktop application does not support drag-and-drop of .msg files (it only returns metadata and not the actual email content), this feature replaces drag-and-drop with a guided Import Outlook Email workflow. The user selects a folder in the tree panel and clicks the Email (Import) icon in the toolbar. The icon remains disabled until a folder is selected. Once clicked, the system verifies whether the user is already authenticated with Microsoft. If not, a Microsoft login window (via MSAL) prompts the user to sign in. After successful authentication, the system fetches emails from the user's Outlook inbox using Microsoft Graph loading them in batches of five at a time with infinite scrolling. The email list dialog displays each email as a card showing the subject, sender, received date, and a checkbox for selection. The user can select one or multiple emails and click Import. During the import, the system retrieves complete email data (full MIME content, body, attachments, recipient lists, metadata) and generates a .eml file for each selected email. Files are saved into the selected folder, and duplicate filenames are automatically handled by appending counters (e.g., (1), (2), etc.). If the destination folder is mapped to the database (tbFolders), each imported email should also be stored in Database (tbFiles) table and a detailed notes entry should be created in tbFileNotes table for that file capturing metadata such as subject, sender, recipients, received date, attachment details, and email content. These notes appear in the Notes panel and are accessible through file click from the file panel, just as in the existing application. Live Progress Tracking: During the import process, the application displays a real-time progress indicator showing: -> how many emails have already been imported, and -> the total number of emails selected for import (e.g., 3/10 imported). This gives the user clear visibility into the ongoing import process and improves the overall user experience. After all imports are completed, the dialog closes automatically and the application refreshes the selected folder in the tree panel so the newly imported .eml files appear instantly. Note: Files & notes can only be possible to stored in DB when parent folder is stored to DB (tbFolders table). Also, notes can only stored in db if file in which we are adding note is stored in db (tbFiles & tbFileNotes).
|  | Saving Email | <Same form as "Copy Files"> | User shall be able to save files by dragging the selected email to the desired destination. | Done
|  | View Email |  |  | Done
|  |  | Select Email |  | Done
|  |  | Read Email |  | Done
|  |  | Tooltip | User shall be able to view the emails via info pop-up button in the same column. | Done
|  |  | Notes Column | User shall be able to view the emails in notes column on selection. | Done
|  | Display EXIF data |  | User shall be able to view the EXIF data of selected images on the system. | Done |  | ok
|  |  | Select File Info | User shall be able to seelct the file info options and view the EXIF data of selected image. | Done |  | ok
|  | Favourites tab |  |  | Done |  | ok
|  |  | Create Favourites | User shall be able to create favourites by right clicking the selected folder and selecting "Add to Favourties" button. | Done |  | ok
|  |  | View Favourites | User shall be able to view the favourite items by opening the tab under left menu panel. | Done |  | ok
|  | Search |  | User shall be able to search Projects' database for desired files. The search function shall allow the user to also search for content in emails and notes. | Done |  | ok
|  |  | Search Options | User shall be able to search as per selected criteria i.e., current folder / entire database. | Done |  | ok
|  |  | Search in current folder |  | Done |  | ok
|  |  | Search in entire database |  | Done |  | ok | Fast result with option full database
|  |  | Add Keyword |  | Done |  | ok
|  |  | Filter for files & documents |  | Done |  | ok
|  |  | Activate file filter | Checkbox | Done |  | ok
|  |  | Created from & to dates | Date Picker | Done |  | ok | Please change date format to current country settings | Done
|  |  | Modified from & to dates | Date Picker | Done |  | ok | It seems, the result do not filter by create date | Done
|  |  | Filter for folders |  | Done |  | ok
|  |  | Activate Address filter | Checkbox | Done |  | ok | ID in address (addrNo) window does not compare with db ID | Done
|  |  | Action buttons |  | Done |  | ok
|  |  | Search |  | Done |  | ok
|  |  | Cancel |  | Done |  | ok
|  |  | Close |  | Done |  | ok
|  |  | Restriction options | User shall have the functionality to restrict the search to defined database, folder and files as per checkbox selection under folder hierarchy. | Done | Documents filter is disabled because the document panel currently has no data, as it is only usable with the Layout Manager plugin, which is out of scope.
|  |  | View Search data | User shall be able to view a table for found items as per search options, filters and restrictions. | Done |  | ok
|  |  | Name | Column 1 | Done |  | ok
|  |  | Number | Column 2 | Done |  | ok
|  |  | Type | Column 3 | Done |  | ok
|  |  | Path | Column 4 | Done |  | ok
|  | Address Management |  | User shall be able to assign specific company or customer addresses to individual projects. | Done |  | ok
|  |  | Select Options | User shall be able to find out which file is stored for the addresses. | Done |  | ok
|  |  | Database | User shall be able to select & configure the database for specific addresses. | Done |  | ok
|  |  | Configure / Select Database | User shall be able to configure or select the database. | Done |  | ok
|  |  | Settings |  | Done |  | ok
|  |  | Ignore local drive | Checkbox | Done |  | ok
|  |  | Report file changes | Checkbox | Done |  | ok | Please disable by default | Done
|  |  | Folder update interval | Numerical text box | Done |  | ok
|  |  | File update interval | Numerical text box | Done |  | ok
|  |  | Cache |  | Done |  | ok
|  |  | Use cache for directories | Checkbox | Done |  | ok
|  |  | Copy cache file from other Db (if available) | Checkbox | Done |  | ok
|  |  | Action buttons |  | Done |  | ok
|  |  | Save |  | Done |  | ok
|  |  | Cancel |  | Done |  | ok
|  |  | Ok |  | Done |  | ok
|  |  | Address Search | User shall be able to search the addresses. | Done |  | ok | Cannot move the address window | The Address window is movable , Please try moving it using the top edge/header area of the dialog.
|  |  | Search Details |  | Done |  | ok
|  |  | Search Text | Textbox | Done |  | ok
|  |  | Company | Textbox | Done |  | ok
|  |  | City | Textbox | Done |  | ok
|  |  | Address no. | Textbox | Done |  | ok
|  |  | Role Selection | Dropdown | Done |  | ok
|  |  | View Search data | User shall be able to view the data in table view. | Done |  | ok
|  |  | ID | Column 1 | Done |  | ok | ID should show the ID number and not AddrNo | Done
|  |  | Company Name | Column 2 | Done |  | ok
|  |  | First Name | Column 3 | Done |  | ok
|  |  | Street | Column 4 | Done |  | ok
|  |  | Postal code | Column 5 | Done |  | ok
|  |  | City | Column 6 | Done |  | ok
|  |  | Add / Edit address details | User shall be able to add new address or edit an existing address. | Done |  | ok
|  |  | Address no. | Numerical text box | Done |  | ok | ID should show the ID number and not AddrNo or AddrNo as separate field | Done
|  |  | Deleted checkbox | Checbox | Done |  | ok
|  |  | Address Type | Dropdown | Done |  | ok
|  |  | Salutation | Dropdown | Done |  | ok
|  |  | Name / Company | Textbox | Done |  | ok
|  |  | First Name | Textbox | Done |  | ok
|  |  | Suffix 1 | Textbox | Done |  | ok
|  |  | Suffix 2 | Textbox | Done |  | ok
|  |  | Suffix 3 | Textbox | Done |  | ok
|  |  | Suffix 4 | Textbox | Done |  | ok
|  |  | Street | Textbox | Done |  | ok
|  |  | PO Box | Textbox | Done |  | ok
|  |  | Postal code | Numerical text box | Done |  | ok
|  |  | Country | Textbox | Done |  | ok
|  |  | Region | Textbox | Done |  | ok
|  |  | Language | Textbox | Done |  | ok
|  |  | Date of birth | Date Picker | Done |  | ok | date format is correct here | But from now on, the date format will be taken directly from the Windows system settings and displayed accordingly throughout the application.
|  |  | Salutation | Dropdown | Done |  | ok
|  |  | Address grouping | User shall be able to view address groups they have added. Also, user shall be able to add new addresses into address groups. | Done |  | ok
|  |  | Group | Column 1 | Done |  | ok
|  |  | Group description | Column 2 | Done |  | ok
|  |  | Define Dependent Address | User shall be able to define the dependent addresses via add /edit address details. | Done |  | ok
|  |  | Add | User shall be able to add dependent addresses. | Done |  | ok
|  |  | Remove | User shall be able to remove dependent addresses. | Done |  | ok
|  |  | Assign address | User shall be able to assign specific addresses to projects using below flow: right click on context menu -> select properties -> select address group -> double click on architect | Done |  | ok
|  |  | Ok |  | Done |  | ok
|  |  | Save |  | Done |  | ok
|  |  | Cancel |  | Done |  | ok
|  | Language Settings (Tools) |  | User shall be able to select preferred language i.e., German OR English. | Done |  | ok | New ok, import ok, how to delete a specified column? copy column ok. Wrong column names in message | Done
|  |  | Add new language | User shall be able to click on "+" button to add new language | Done |  | ok | Had an error while importing from other table | Done
|  |  | Edit translations | User shall be able to double click on the cell from below table and edit translations. | Done |  | ok | After adding a new language, it was not able to use table with legacy programs anymore. Maybe incompatible xml format? | Done
|  |  | View | Table view with original and desired language components. | Done |  | ok
|  |  | ID | Column 1 | Done |  | ok
|  |  | Keyword | Column 2 | Done |  | ok
|  |  | Component | Column 3 | Done |  | ok
|  |  | Original | Column 4 | Done |  | ok
|  |  | German | Column 5 | Done |  | ok
|  |  | Desired Language | Column 6 | Done |  | ok
|  |  | Save changes |  | Done |  | ok
|  | Permissions Management (Tool) |  | User shall be able to manage the permissions on Antlog's Projects. | Done
|  |  | Add new password | User shall be prompted to create new password at the time of 1st time selection of permission options. | Done
|  |  | Add password to access | User shall have the functionality to add password before accessing permission options every time they open this tool. | Done
|  |  | Add user group | User shall be able to click on "+" button to add new user groups. | Done
|  |  | Add users | User shall be able to click on "+" button to add new users under selected user groups. | Done
|  |  | View permissions (Apply Permission) | User shall be able to view the permissions of selected user / user groups. | Done
|  | Project Manager Options (Tool) |  | User shall be able to manage plugins and other critical options from this tool. | Done |  | ok | When I changed something, message should call "Starting Project Manager". Antlog is the name of the company | Done
|  |  | Activate plugins | User shall be able to select the plugins they want to activate and select them. Once selected, user shall be able to access plugins on restarting the Projects application. | Done |  | ok
|  |  | Layout Manager | Checkbox | Done | It is currently disabled as it is not in use, since AutoCAD-related plugins are out of scope.
|  |  | Layer Convert | Checkbox | Done | It is currently disabled as it is not in use, since AutoCAD-related plugins are out of scope.
|  |  | Comparison | Checkbox | Done |  | ok
|  |  | Reports | Checkbox | Done |  | ok
|  |  | Settings |  | Done
|  |  | Text | User shall be able to manage font and their sizes for the system. | Done |  | ok | When I enter some chars in field, style names should be filtered or jump to... | Done
|  |  | Text style menu | Dropdown | Done |  | ok | Menu do not change the text style | The legacy application does not change the menu style dynamically. The same behavior is currently being followed here as well.
|  |  | Tree text style | Dropdown | Done |  | ok
|  |  | List text style | Dropdown | Done |  | ok
|  |  | All text style same as menu | Checkbox | Done |  | ok
|  |  | Style |  | Done
|  |  | List view with lines | Checkbox | Done |  | ok
|  |  | use default values for columns | Checkbox | Done |  | ok
|  |  | Toolboxes can be removed | Checkbox | Done |  | ok
|  |  | Turn on transparency when inactive | Checkbox | Done |  | ok
|  |  | File list |  | Done
|  |  | Check modification date between file & database | Checkbox | Done |  | ok | Change the setting do not refresh the file list | Already Working, but need to confirm from your side .
|  |  | Show folders is file list as default | Checkbox | Done |  | ok
|  |  | Logfile |  | Done
|  |  | Enable Log | Checkbox | Done |  | ok
|  |  | Delete record after days | Textbox | Done |  | ok
|  |  | Logfile location | Label | Done |  | ok
|  |  | Action buttons |  | Done
|  |  | Save |  | Done |  | ok
|  |  | Cancel |  | Done |  | ok
|  |  | Ok |  | Done |  | ok
|  |  | Project Preferences | User shall be able to select the project preferences from available options. Using this, user shall be able to select a template folder whose contens shall be automatically copied to new project folders. | Done |  | ok | Template folder setting was not imported by db - tbFolder, Column Template | Its now added will imported once you get the next releaase
|  |  | Copy contents to new project | Selection button | Done |  | ok
|  |  | Copy contents to new subproject | Selection button | Done |  | ok
|  |  | Search field size | Textbox | Done |  | ok
|  |  | Search drop down size | Textbox | Done |  | ok
3 | Setup Installer |  |  |  | Done
BE, Others
1 | Setup |  |  |  | Done
Environment, Unified Db setup on app startup for Postgres/MSSQL (Merged Standard & Address database tables to single DB), and Windows App (.exe)
2 | Database History & Migration of existing DB(s) to new Unified DB |  |  |  | Done
|  | Select Database |  | Add toolbar option to select a database. | Done |  | ok
|  | Open Existing Database (Upload) |  | Allow users to upload and open an existing database file using this icon. | Done |  | ok
|  | Create New Database |  | Implement functionality to create a new database from scratch. | Done |  | ok
|  | Select SQL Database |  | Enable connecting to a SQL Server database. | Done |  | ok
|  | Select Postgre Database |  | Enable connecting to a Postgre database. | Done |  | ok
|  | Delete Selected Entry |  | Allow users to delete selected database entry from the list or UI. | Done |  | ok
|  | Settings Dropdown |  | Implement settings icon with dropdown options containing 6 settings options. | Done |  | ok
|  | Import from ACCDB |  | Add import functionality for Microsoft Access (.accdb). | Done
|  | Import from OLD MDB |  | Add import functionality for legacy (.mdb) files. | Done
|  | Import from MS SQL |  | Add import functionality for Microsoft SQL databases. | Done |  | ok
|  | Import from MySQL |  | Add import functionality for MySQL databases. | Done
|  | Import from Postgre |  | Add import functionality for Postgre databases. | Done
|  | Import from Autodesk ProductStream |  | Add three sub-options under Autodesk ProductStream import. | Out of scope | It is depended on Autodesk.
|  | Import Only Year |  | Sub-option to import only specific year data. | Out of scope | It is depended on Autodesk.
|  | Skip Existing Project Folder |  | Sub-option to skip existing project folders during Autodesk import. | Out of scope | It is depended on Autodesk.
|  | Search Drawing Without Project |  | Sub-option to search drawings not linked to any project. | Out of scope | It is depended on Autodesk.
3 | Licensing & Registration |  |  |  | Done
4 | Windows OS |  |  |  | Done
5 | Application Shortcut Keys |  |  | Add keyboard shortcuts for quick navigation and actions. | Done |  | ok
6 | Application Menus |  |  |  | Done
|  | File |  |  |  |  | ok
|  |  | Close Menu | Quite all Application Instances |  |  | ok
|  | Edit |  |  |  |  | ok
|  |  | Add Note | Add Note for selected file/folder |  |  | ok
|  | Option |  |  |  |  | ok
|  |  | Language Settings |  |  |  | ok
|  |  | Options |  |  |  | ok
|  |  | Permits |  |  |  | ok
|  |  | Addresses |  |  |  | ok
|  |  | Register Software |  |  |  | ok
|  | Network |  |  |  |  | ok
|  |  | Connect/Disconnect Drive |  |  |  | ok
7 | Preserve Application states |  |  | Implement autosave of layout, last opened folder and preferences and restore on application open. | Done |  | ok
8 | Data table column resize, rearrangement and sorting (ASC/DESC) |  |  |  | Done |  | ok
9 | Software Registartion |  |  | Software Registration with licence handling (Register, Re-Register and Re-New Licence) | Done | Integrated Existing application DLLs (Flow) | ok
Plugins
1 | Reporting (plugin) |  |  | This plugin allows the user to develop, compile, & print their own lists. | Done | Integrated Existing application DLLs (Flow) | ok
Create Report Forms
White-labelling
|  | Templates |  | Standard templates info to be provided by Antlog and Azilen to implement the same as per basic complexity.
Projects Overview
Project Details
Resource Allocation
Cost Report
2 | Comparison & Synchronization (plugin) |  |  | This plugin helps the users to compare file contents of folders & subfolders | Done | Integrated Existing application DLLs (Flow) | ?? | please add animation while loading
Folder & Subfolder detection
Folder & Subfolder comparison
|  | Logs |  | Logs of missing / changed files & sub-folders available for users.
Date
|  | Folder & Subfolder selection |  | User can do selection for sync.
Folder & Subfolder copy
Folder & Subfolder deletion
3 | Drawing Management (Layout Manager Plugin) |  |  |  | Out of scope
4 | Layer Convert |  |  |  | Out of scope
Performance Improvements
1 | Database Migration Performance optimization |  |  | Speed up database migration for MSSQL/Postgres/MySQL/ACCBD/MDB Databases | Done |  | ok
2 | Tree panel Performance optimization |  |  | Prevent application lag or freezing when handling large folders. | Done |  |  | Still slow with large db.
3 | File panel Performance optimization |  |  | Prevent application lag or freezing when handling large lists of files and subfolders across all views (Detail, List, Large Icons, Small Icons, Align). | Done |  | ok
4 | Note panel Performance optimization |  |  | Prevent application lag or freezing when handling a large number of notes. | Done |  | ok
5 | Search Module Results optimization |  |  | Prevent application lag or freezing when handling large search result sets, and ensure smooth navigation to files or folders from the search panel. | Done |  | ok
6 | Copy/Paste Module optimization |  |  | Start copy/paste operations immediately for large folders containing data in GBs. | Done |  | ok
7 | Project List Module optimization |  |  | Prevent application lag and blank screens in dialogs when handling a large number of areas, projects, or sub-projects. | Done |  |  | open fast but load slow. user has no animation or info when loading proceed | Done
8 | load tree/file panel on app startup immediatly |  |  | Reduce wait time for loading tree and file panel data during application startup. | Done |  | ok
9 | Multi-Select Operations Performance optimization |  |  | While Performing some operation in Tree/Files/Notes panel with Multi-selecting application should work smoothly and User should be able to perform other operations. | Done |  | ok

## Test-Notes
No | Theme | Date | Note | Pending | Solved-Tested | Ralf's Comment | Dev-Tested | Dev Comments | Image | Need to Work On(DEV-TEAM)
1 | Folder view | 2026-03-02 | In the "Files" field, please use "Show Folders" as the default. |  | 21/04/26
2 | SQL | 2026-03-02 | I cannot connect to an external SQL server. The local connection works. |  | 21/04/26
3 | SQL | 2026-03-02 | The local database cannot be selected in the import window (see video) if there are more than two entries. |  | 21/04/26
4 |  | 2026-03-02 | I left the program window open for some time. The window was white and empty and could not be closed. |  | 21/04/26
5 |  | 2026-03-02 | Import: The "Initialization" animation ran for a very long time before the import started. After 2 hours, I stopped without importing any data. |  | 21/04/26
6 |  | 2026-03-02 | The fast search should also include the "Remarks" field. |  | 21/04/26
7 |  | 2026-03-02 | The search should jump to the match in the folder and file area. |  | 21/04/26
8 |  | 2026-03-02 | The file list loses focus when refreshing. |  | 21/04/26
9 |  | 2026-03-02 | When saving options, the message "You must restart..." appears, even though it is not necessary. |  | 21/04/26
10 |  | 2026-03-02 | The software is extremely sluggish when clicking on a folder. It takes a long time for the list to update. | 21/04/26 |  | Performance with large DB. New Comparison: With the new full size db are "fast search" and "favorites click" much slower then with the reduced db | 28/04/26 | We have implemented fixes for performance improvements, and you will be able to see these changes in the next release.
11 |  | 2026-03-02 | The "New Folder" window takes 3 seconds to open. |  | 21/04/26
12 |  | 2026-03-02 | New folder and new file OK. |  | 21/04/26
13 |  | 2026-03-02 | The "Address Search" tab should be active when assigning an address. |  | 21/04/26
14 |  | 2026-03-02 | The display showing "xx GB free of..." is inaccurate by a factor of 10. | 21/04/26 |  |  | 28/04/26 | Query :- We reviewed the old system and noticed that it displays either two or three digits after the decimal point in different cases. Could you please confirm the expected behavior so we can implement it accordingly? The issue has been resolved, and it is now working perfectly for the three digits after the point in the previous build as well. DONE |  | we have to follow the simillar behaviour same like windows sysytem to show size in footer GB, TB , etc,.. DONE
15 |  | 2026-03-02 | What does the "Status Display" section under the Folder field show? |  | 21/04/26
16 |  | 2026-03-02 | Drag-drop works. |  | 21/04/26
17 |  | 2026-03-02 | The Delete key doesn't work. |  | 21/04/26
18 | dragdrop file | 2026-03-02 | A warning should appear when moving folders or files if database entries might be lost. For example, if a file is moved to a folder that is not stored in the database. |  | 21/04/26
19 | dragdrop file | 21/04/26 | After quited the message (above) with yes, the field «copy with data» must be disabled | 21/04/26 |  |  | 28/04/26 | Query :-Currently, the “Copy with Data” option is disabled when moving folders, but it remains enabled when moving files to an unsaved folder. Should we apply the same behavior for file moves as well (i.e., disable it like in folder move)? DONE |  | DONE
20 |  | 2026-03-02 | Import: As discussed, further imports should be possible at any time. The user should be able to decide which data to keep, overwrite existent data or ignore double record. |  |  | Not tested yet
21 |  | 2026-03-02 | The "Show all files/folders" selection is not saved. |  | 21/04/26
22 |  | 2026-03-02 | Search: The search results should be displayed automatically. |  | 21/04/26
23 |  | 2026-03-02 | Moving the search window either doesn't work at all or is extremely slow. |  |  | see 55 | 28/04/26 | We have resolved the performance issue, and in the next release you will be able to move the search dialog smoothly.
24 |  | 2026-03-02 | Clicking on a search result should display the folder (focus). |  | 21/04/26
25 |  | 2026-03-02 | When typing a search term, it takes 2 seconds for the text to become visible. |  | 21/04/26
26 |  | 2026-03-02 | The EXE file uses 14% of the processor power and over 2GB of RAM while idle! Memory usage is constantly increasing. |  | 21/04/26
27 |  | 2026-03-02 | Exception folders should be defined and saved as defaults, e.g., #recycle. | 21/04/26 |  | 28/04/26 | 28/04/26 | Query :- We have implemented this, and the recycle bin is visible with a red cross icon. Could you please confirm if this indicates that it is already stored in the database or that it cannot be stored? As per our understanding in the new system, system folders like the recycle bin are not saved in the database and are therefore shown with a red cross icon. DONE |  | system file/folder will be hidden,(access denied ,etc,..) same like windows system DONE
28 |  | 2026-03-02 | An animation is needed while the search process is running. |  | 21/04/26
29 |  | 2026-03-02 | The search window cannot be closed. |  | 21/04/26
30 |  | 2026-03-02 | When the program starts, 4 EXE files are launched in the Task Manager. Why? |  | 21/04/26
31 |  | 2026-03-02 | When the yellow information window opens, the selected file is covered. In this case, the area should be moved. |  | 21/04/26
32
33 |  | 2026-03-02 | Plugin interface with registration (Ant_Reg2.exe) |  | 21/04/26
34 |  | 2026-03-02 | Image preview (possible for other documents?) |  | 21/04/26
35 |  | 2026-03-02 | F2 key to open properties |  | 21/04/26
36 |  | 2026-03-02 | Object selection with Shift key (Ctrl works) |  | 21/04/26
37
38 |  | 2026-03-02 | How can I set up a new PostgreSQL database or install PostgreSQL? |  |  | Test pending
39 |  | 2026-03-02 | Where are the registry entries stored? The correct location would be: Computer\HKEY_CURRENT_USER\SOFTWARE\ANTLOG e.g., \PRJ (Old version: \Documents) |  | 21/04/26 | Where are the settings saved? | 28/04/26 | Alredy diacussed ! We are storing this in AppData |  | we need to provide list of settings to Ralf
40 |  | 2026-03-02 | Naming conventions: Please always save system information in English: Registry, System files, File system |  | 21/04/26
41 |  | 2026-03-02 | Product name: ANTLOG-Projects or PRJ |  | 21/04/26
42 |  | 2026-03-02 | Publisher: ANTLOG AG |  | 21/04/26
43 |  |  |  |  | 21/04/26
44 |  | 2026-04-03 | After new installation, all Test is terrible small. By default, we have size 9 |  | 21/04/26
45 |  | 2026-04-03 | Text size can not be changed in options |  | 21/04/26
46
47 | SQL Import | 17/04/26 | It seems that not all data was imported. See imported data - original data tbFolders: 2964 - 3558 tbFiles: 70171 - 70668 tbDocuments: 6014 – 13574 | 2026-12-05 |  | I imported again with the option "ignore missed files". In the column "Num" still was missed the most records (see picture). Then I created a new database and importet all again. Now the numbers are here. The import should complete missed data of existant records. Then I compared the numbers of records. Please check the big difference in table tbDocuments. | 13/05/26 | The number columns were previously being ignored, but they have now been included. The changes will be available in the next release. According to the duplicate-checking functionality, duplicate records are intentionally ignored during import. The system validates records within the source database, and if a duplicate entry is found, it is skipped during the import process. Please confirm whether this is the expected behavior from your side. If you would still like us to verify the exact duplicate data being skipped, please provide the database backup so we can analyze how many duplicate records exist and confirm that the same duplicate entries are being ignored during import. . |  | The number columns were previously being ignored, but they have now been included. The changes will be available in the next release. According to the duplicate-checking functionality, duplicate records are intentionally ignored during import. The system validates records within the source database, and if a duplicate entry is found, it is skipped during the import process. Please confirm whether this is the expected behavior from your side. If you would still like us to verify the exact duplicate data being skipped, please provide the database backup so we can analyze how many duplicate records exist and confirm that the same duplicate entries are being ignored during import. .
48 | SQL Import | 17/04/26 | tbFolders: All records have CreateDate an ChangeDate the date of import instead the original date |  |  |  | 28/04/26 | Already done ! This has been fixed in our updated bulk import pipeline, which directly inserts records with the original CreateDate and ChangeDate values preserved from the source database. Resolution: We can re-run the import using the corrected pipeline, which will preserve all original dates. No data will be lost — the system will detect existing records and only update the affected date fields.
49 | SQL | 17/04/26 | Database is not relational. I killed so many folder records ant this did not reduced the records of tbFiles |  |  | Not an issue, just a question | 28/04/26 | The database intentionally does not enforce foreign key constraints between folders and files — this is inherited from the original application's architecture. However, our application handles this at the code level: when you delete a folder through the standard folder operations, the system automatically removes associated file records first. If you observe orphaned file records, it is likely due to files that were saved with a different parent folder reference, or files that were imported/created before the folder was tracked in the database. This is not a data integrity bug — it is the expected behavior matching the original application."
50 | SQL | 17/04/26 | I reduced the amount of records to a little bit more then the half. With this, the performance is good to work as first. With a few clicks, the program gets slower and slower. |  |  |  | 28/04/26 | We have resolved the performance issue, and in the next release you will be able to see all releted changes
51 | Fast search | 17/04/26 | When you click into field “fast search” the content should be marked to be replaced with a new search string |  |  |  | 28/04/26 | DONE
52 | Fast search | 17/04/26 | The newest record must be on top (sort by last change) |  |  |  | 28/04/26 | DONE old_antl\Projects.NET4\Projects.NET4\ANTLOG Projects\ANTLOG Projects\ctrlTreeView.vb, the FastSearch method uses Id DESC for sorting. Here is the exact line of code (Line 2056): |  | need to check order of search results. for better result :- The Ideal Solution: Sorting by ChangeDate To make sure renamed or modified folders jump to the top, we should use the ChangeDate column. In your database, the tbFolders table has a ChangeDate field. If the application is configured to update this field whenever a folder is renamed or moved, we can change the sort order in the code: Instead of: order: [['Id', 'DESC']] We would use: order: [['ChangeDate', 'DESC'], ['Id', 'DESC']] DONE
53 | Folder view | 17/04/26 | Default sort: must show folders first, then alphanumeric |  |  |  | 28/04/26 | DONE |  | need to check this scenario and as per the old and windows system the folder should be at the top in the file panel when we do sorting
54 | Folder view | 17/04/26 | If folders or files have special chars as “_”, they must be ordered on top, same as explorer does |  |  |  | 28/04/26 | Symbol Priority: Folders or files starting with symbols like _, $, or . are now prioritized at the top of their group. In your C:\ folder, this means $DEE... and _hey will correctly appear before the A folders. DONE |  | Symbol Priority: Folders or files starting with symbols like _, $, or . are now prioritized at the top of their group. In your C:\ folder, this means $DEE... and _hey will correctly appear before the A folders.
55 | Search file | 21/04/26 | The Search Window cannot be moved to see the content behind |  |  |  | 28/04/26 | We have resolved the performance issue, and in the next release you will be able to move the search dialog smoothly.
56 | Folder view | 21/04/26 | When a file was deleted by explorer but record is visible. Record cannot be deleted |  |  |  | 28/04/26 | DONE |  | If a file is not present in the file system but exists in the database, it should still be deletable from the file panel. Deleting it should remove the corresponding database entry.
57 | Folder view | 21/04/26 | When the window for new folder opens, the field Name must be actiated |  |  |  | 28/04/26 | Pendding |  | need to change the icon for the name field in folder properties dialouge .
58 | Folder view | 21/04/26 | After entering a new name for a folder, Enter key must have the same effect as OK |  |  |  | 28/04/26 | DONE
59 | System | 21/04/26 | It seems the program is 64 Bit. Why the application folder is under «Program Files (x86)»? |  |  |  | 28/04/26 | Query Discussed |  | We are using existing DLLs which are 32 bit pnly so that's why we have used I(X86) folder to install depenmdecies. Please update ypu DLLs to 64 bit anmd provide it to us so after that only we can check and update path if it's working.
60 | System | 21/04/26 | We sign our exe files with a certificate from Digicert. I should sing the exe files before your crate the setup or I create the setup by myself |  |  |  | 28/04/26 | You can create the setup by yourself if you already have the certificate and signing process. Otherwise, we can create the setup and send it to you, then you sign the final setup exe before distribution. |  | Yes, that will help. Since the warning appears when running the final setup `.exe`, the final installer should be signed with your DigiCert certificate. Best approach: I will create the unsigned setup from Electron Builder and share it with you. Then you can sign the final setup `.exe` using your DigiCert certificate before sharing it with users.
61 | Folder view | 21/04/26 | Operation via buttons: Pressing the left key should close the active folder. Pressing it again should switch to the parent folder. |  |  |  | 28/04/26 | DONE
62 | Folder view | 21/04/26 | Switch «show projects» needs a long time. Need a animation to let user know, program is working |  |  |  | 28/04/26 | Already done !
63 | File view | 21/04/26 | Press a char should switch to the next content, beginning with this char. Files and folders view |  |  |  | 28/04/26 | DONE
64 | Project list | 21/04/26 | If loading the list needs long time, there is an animation needed |  |  |  | 28/04/26 | DONE
65 | Folder view | 22/04/26 | Moving folders: The window must close when finish. Please aktivate «Close after finish» as default |  |  |  | 2026-04-05 | DONE
66 | Folder view | 22/04/26 | The option selection «Close after finish» must be saved |  |  |  | 2026-04-05 | DONE
67 | Folder view | 22/04/26 | If a folder was moved by another user, the list must acutalize after a few seconds |  |  |  | 2026-05-05 | Query Discussed :-need to enable the auto refersh for this because the legacy application behaves same like this .
68 | Folder view | 22/04/26 | If a folder was moved, not the destination folder must be selected. Focus shoud keep on current folder |  |  |  | 2026-05-05 | Query Discussed:- In the legacy application, when a folder is moved, the selection shifts to the destination folder. The same behavior is followed here. DONE |  | DONE Will implement according to the requirement you mentioned — the destination folder will not be focused automatically; only the destination folder node will expand.
69 | Folder view | 22/04/26 | When I just close a folder with the arrow symbol, it must not be activated |  |  |  | 2026-05-05 | Query Discussed |  | DONE So, when the folder is expanded/collapsed using the arrow icon, the folder should not get selected automatically. The folder should only be selected when the user clicks on the folder row itself.
70 | Folder view | 22/04/26 | I try to delete a folder, which is a project. He does not disappear |  |  |  | 2026-05-05 | Already Working, but need to confirm from your side .
71 | Folder view | 22/04/26 | The setting «copy content to new project» was not migrated with import database (saved in tbFolders, Template) |  |  |  | 2026-05-05 | DONE
72 | Folder view | 22/04/26 | The date format must use the current local format (now 22-04-206, current is 22.04.2026) |  |  |  | 2026-05-05 | Query Discussed: In the legacy application, when the date format is changed in Windows system settings, only the date separator (symbol) is updated, not the entire date format. Is this the expected behavior? |  | DONE We need to update the date format from a static UI format to a dynamic format. When the user changes the date format in Windows settings, the same format should be reflected across all panels in the application.
73 | Folder view | 22/04/26 | Moving files: If I move files to as subfolder in a project, I get the warning. If one folder is not saved in database, the data must linked to its parent folder if it is a project or subproject |  |  |  | 2026-05-05 | Query Discussed |  | DONE When moving files, if the file’s immediate parent folder is not available in the database, the system should search upward in the folder hierarchy and link the file to the nearest available parent folder that exists in the database. In this case, the memberOf column should reference that nearest database folder. If no folder in the hierarchy exists in the database, then the system should show the existing data loss warning. Otherwise, if a valid nearest parent folder is found, the file should be linked to that folder instead of showing the warning.
74 | Folder view | 23/04/26 | Drag-drop from a zip file (winRar) do not work |  |  |  | 2026-05-05 | Already Working, but need to confirm from your side .
75 | Folder view | 23/04/26 | After many hours of useing (over night opened), the computer was nearly blockd by PRJ. |  |  |  | 2026-05-05 | Already Working, but need to confirm from your side .
76 | Folder view | 23/04/26 | One folder do not shows file size and date: C:\Users\rm\Downloads\ - after the second load, the info was visible |  |  |  | 2026-05-05 | Already Working, but need to confirm from your side .
77 | Fast search | 23/04/26 | If I press Enter key in fast search and the result already switch to folder, the combo should close |  |  |  | 2026-05-05 | DONE
78 | Fast search | 23/04/26 | When I click to other part with the mouse, the combo should close |  |  |  | 2026-05-05 | DONE
79 | Fast search | 23/04/26 | If I enter a search string and there is no match. The combo with the previous search results should be cleared |  |  |  | 2026-05-05 | DONE
80 | DB Import | 23/04/26 | Some project folders do not have a project number. These data was not imported properly | 2026-12-05 |  | See number 47 | 2026-05-05 | Query Discussed |  | The NUM columns were previously being ignored, but they have now been included. The changes will be available in the next release. According to the duplicate-checking functionality, duplicate records are intentionally ignored during import. The system validates records within the source database, and if a duplicate entry is found, it is skipped during the import process. Please confirm whether this is the expected behavior from your side. If you would still like us to verify the exact duplicate data being skipped, please provide the database backup so we can analyze how many duplicate records exist and confirm that the same duplicate entries are being ignored during import. .
81 | File view | 23/04/26 | Selection with shift key do not work proper: Click upper file to select, press shift key and press arrow down key. This do not select anything |  |  |  | 2026-06-05 | DONE
82 | File view | 23/04/26 | I had the situation that keys as F2 and DEL had no more effect. With closing and opening again it was working again |  |  |  | 2026-06-05 | DONE
83 | File view | 23/04/26 | Show folder size: Many times process stops after 2-3 folders. When I change folder, sometimes nothing will calulate, when I switch to other folder an come back, then it calulate fast and correct. |  |  |  | 2026-05-05 | Already Working, but need to confirm from your side .
84 | File view | 23/04/26 | File size often shown as 0 KB |  |  |  | 2026-05-05 | In the legacy Antlog application, a file appear as 0 KB because its size is very small (in bytes), and it gets rounded down when displayed in KB. |  | Ralf will review this and provide an update soon.is it okay when the file size in bytes and its shows 0kb
85 | Favorites | 24/04/26 | The favorites list must be sorted by name |  |  |  | 2026-05-05 | DONE
86 | Folder view | 24/04/26 | Folder properties «Advanced» has no function |  |  |  | 2026-05-05 | Query Discussed |  | DONE Keep the current behavior as it is. Since the Advanced function does not have any functionality at the moment, the button should remain visible but appear disabled with a gray color.
87 | File view | 29/04/26 | While testing and try to delete a file, computer was fully busy by PRJ2 - CPU 81%, RAM 8GB |  |  |  | 2026-05-05 | Already Working, but need to confirm from your side .
88 | File view | 29/04/26 | Cannot drop file from PRJ to Outlook as an attachement |  |  |  | 2026-05-05 | Confirmed |  | The email integration approach has now changed, so end users will no longer be able to drag and drop emails directly from Outlook.
89 |  | 2026-08-05 | File properties of a msg file show wrong window |  |  |  | 2026-08-05 | DONE
90 |  | 2026-05-12 | Option "Profile" missed | 2026-12-05 |  | There is no Record in Database tbTemplates. Anyway there is the filename in field "Profile". The database records of templates was imported but not listed on options window | 13/5/26 |  |  | Under Testing In the existing code of the legacy Project Manager application, the Profile field in the Template Creation tab does not contain any data to display. The code currently sets ComboBoxProfile.SelectedIndex = 0, which indicates that the dropdown remains empty. We just need confirmation on whether we should follow the same behavior for the Create File Template dropdown in the Options → Template tab Profile field.
91 | Folder view | 2026-05-12 | Cannot delete folder | 2026-12-05 |  |  | 13/5/26 | Already Working, but need look for your scenario and to confirm from your side . | r | Already Working, but need look for your scenario and to confirm from your side .
92 | Folder view | 2026-05-12 | Wrong name in dialog "0" instead foldername | 2026-12-05 |  |  | 13/5/26 | Already Working, but need look for your scenario and to confirm from your side . |  | Already Working, but need look for your scenario and to confirm from your side .

## CAD Plugins Analysis
Module | Steps | Status | Need to check before estimation decision | Approx. Estimation | Implementation Status | UAT Status
6-8 Weeks
Layout Manager
| Integrate Plugin DLL | Checked
Load Layout in Document panel for Drawing files
| Add layouts in MSSQL / Postgres | Checked for MSSQL/Postgres
| Jump to DWG | Checked
Folder Dialog - Layout Manager Tab
| Connect Assigned Address with Layout Properties | Checked
| Option Dialog - Layout Manager Tab | Checked
Layer Convert
| Integrate Plugin DLL | Checked
| Convert Layers for Drawing files | Checked
| Settings | Checked
| Convert Colors | Checked
| Convert Layers | Checked
| Convert Objects | Checked
| Layer Definition | Checked
Open config / Read Objects
Document Panel
| Show Layouts | Checked
| Add Layout | Checked | (Got Serial number for V13 from client side)
| Copy Layout | Checked | (Got Serial number for V13 from client side)
| Delete Layout | Checked | (Got Serial number for V13 from client side)
Filter By Project
Views
New Index
| Properties | Checked
New Note
Multi-select/Sorting/Move columns operations
Permission management (Enable & Check Documents related permissions)
Search Management (Enable Document search)
File Panel
| Create New DWG Autocad File | Checked
Need to check Profile is linked with autocad or not
Note: Please check all the features are covered or not proper estimation

## CAD Plugins Risks
Actions Needed Before Development
ANTLOG needs to provide a full activation key or ANTLOG-One license before development and verification can start properly. Right now we are using the trial version, and some important operations are blocked or limited, such as Load Layout, Add Layout, and other plugin/layout actions. Without a full license, we cannot confirm the real behavior of the plugins. (For V13 as per discussion)
Area | Risk / Issue | Can we handle in new app code? | Client / ANTLOG must handle? | Final Comment
Trial license | Trial version blocks operations like Load Layout / Add Layout. | No | Yes | Client must provide activation key or ANTLOG-One license before real plugin testing. (We have V12 Serial number / password, needs V13 serial number / passwords)
Shared registry path | Old and new app both use HKCU\Software\ANTLOG\Documents and subkeys. | No | Yes | We can sync carefully and add guards. Client must confirm whether old and new app are allowed to run together with same registry.
Wrong DB context | Old plugins may read dbpath, dbVersion, SQLConnString from registry. | No | Yes | We can write/clear/block values, but DLL behavior is controlled by ANTLOG DLL.
SQL credentials in registry | SQLConnString may contain username/password for legacy DLL usage. | No | Yes | We can clear after plugin close or avoid when possible, but if DLL requires it, client must accept/update DLL.
Old app + new app together | Both can overwrite each other’s registry state. | No | Yes | We can warn/block if old app process is detected, but true isolation needs client decision or DLL registry path change.
PostgreSQL + DLLs |  | No | Yes | ANTLOG must confirm/update DLLs if PostgreSQL plugin support is required.
Layoutmanager ReadLayouts | Host still invokes legacy ReadLayouts / fallback GetFileDocuments. DLL may internally use registry DB context. | No | Yes | DLL internally needs SQL registry, ANTLOG must update DLL.
Layoutmanager with PostgreSQL | Most risky plugin path for PostgreSQL. | No | Yes | Antlog Must must confirm/update DLLs.
Registry Entries New App Needs To Control These are needed for new app plugin integration:
Registry Path | Values New App Uses | Why Needed
HKCU\Software\ANTLOG\Documents | Tree1, Tree2 | Active folder paths for plugin/report context
HKCU\Software\ANTLOG\Documents | ActiveFrame | Tells plugin which folder panel/frame is active
HKCU\Software\ANTLOG\Documents | xmlPath, Language | Plugin translation/language loading
HKCU\Software\ANTLOG\Translations | Language, xmlPath | Translation compatibility
HKCU\Software\ANTLOG\Documents\Plugins | S1ActivePlugin, S2ActivePlugin | Active plugin per frame
HKCU\Software\ANTLOG\Documents\Plugins | CurrentCAD, AcadTimeout, Initials | CAD/plugin settings for Layoutmanager/LayerConvert
HKCU\Software\ANTLOG\Documents | FoundAcad, FoundGcad, FoundZwPlus, FoundBricscad | CAD detection flags
HKCU\Software\ANTLOG\Documents\Plugins | LayerConvLang, Language | LayerConvert-specific settings
HKCU\Software\ANTLOG\Documents\Layoutmanager | Layoutmanager settings | Layoutmanager-specific behavior
HKCU\Software\ANTLOG\Documents | ReportsFolder, Reportfilechange | Reports output/settings
High-Risk DB Registry Entries These are the risky ones because old/new apps can conflict:
Registry Path | Values | Concern
HKCU\Software\ANTLOG\Documents | dbpath | Old/new app may overwrite current DB path
HKCU\Software\ANTLOG\Documents | dbVersion | Old/new app may change DB type context
HKCU\Software\ANTLOG\Documents | SQLConnString | May point plugin to wrong DB; may contain credentials